## Sheet1
Notes on proposed report
This is a proposal to provide information for Councillors and any other laypersons who are interested in how the Partnership is funded
and how that money is spent.
It is NOT intended as a set of accounts it is merely a simple way of explaining how the Partnership manages its funding
Congleton Partnership Summary Income & Expenditure
April 2020 Opening Balance |  | 54503
Income 2020/21 YTD |  |  |  |  | Project traffic light scheme
CTC Grant 20/21 |  | 15000 |  |  | Green | Project accepted
CEC Grant 20/21 |  | 8000 |  |  | Amber | Needs more work
Youth Forum grants | Inc Trust & YPTrust) | 1050 |  |  | Red | Not taken on.
Walking map launch |  | 379
Cenotaph | (Tesco & Lions)& CTC | 65366 | (CTC £64000)
Total Balance |  | 144298
Expenditure YTD |  | 79739 | (cenotaph £76800)
Balance todate 24.11.20 |  | 64559
Detailed expenditure 2020/21 (YTD 24.11.20) | [5 empty] | outside sources
Allocated
Projects | Project Title | Est Tot Cost | Actual To apr 20 | Actual YTD | Fcst 20/21 onwards | Comments/Outcome | Project Lead
Commited, Proposed, Speculative
C | CSG – Zoom Kit etc | 500 |  | 0 | 500 | ongoing waiting invoice | P.Aston/CSG
C | P Realm – MB Way | 10000 | 6786 |  | 3214 | reserve for future project
C | Youth Forum | 1778 |  | 645 | 1133 | reserve for future project | G.Williams/Youth Forum
C | T.Centre P Realm/Cenotaph | 10000 |  | 0 | 10000 | £7000 Fees & Landscaping ect | M.Smith
C | Play day 2019/2020 | 1400 | 645 | 587 | 168 | 2021-08-01 | J.Money /CCP
C | CSG Green Fare | 687 |  | 0 | 687 | 2021 event 5.6.21 | P Aston/CSG
C | Health and wellbeing fayre | 754 |  | 0 | 754 | 2021 event | S.Firkin /Senior Forum
C | Dementia Group | 5650 | 1928 |  | 3722 | ongoing | D.Ritherdon/DFC
C | Get Involved Bklt | 1000 |  |  | 1000 | ongoing 2021 | J.Money/CCP
C | Active Travel | 500 |  | 500 | 0
C | Admin (ins, adv, website etc) | 1500 |  | 640 | 860 | ongoing | MS
C | Tree Group | 1600 |  | 1393 | 207 | ongoing | M.Gartside/CSG
Sub Total |  | 35369 | 9359 | 3765 | 22245
P (Appendix 1) | Mini Bus drivers | 2000 |  |  | 2000
P (Appendix 1) | Mini Bus Support | 4000 |  |  | 4000
P (Appendix 1) | Tree Planting | 5000 |  |  | 5000
P (Appendix 1) | Recycling Scheme | 2000 |  |  | 2000
P (Appendix 1) | Link Rd Roundabouts | 6000 |  |  | 6000
P (Appendix 1) | Sports pop ups | 8000 |  |  | 8000
P (Appendix 1) | Town Trail | 500 |  |  | 500
P (Appendix 1) | Health & Wellbeing | 10000 |  |  | 10000
P (Appendix 1) | Defribrilators | 5000 |  |  | 5000
P (Appendix 1) | Air Quality project | 500 |  |  | 500
| Elizabeth Group | 5000 |  |  | 5000 | Prime pump statue drive
P (Appendix 1) | Dementia Activity packs | 1000 |  |  | 1000
| Xmas Lights | 1000 |  |  | 1000 | Support Town hall Lighting Xmas 2020
S | Family based projects
S | Enhance Public space
S | Community Food growing
S | Social prescribing
S | Heritage & History
S | Local Business
S | Town Pride
S | Hydro Electric Scheme
S | 2020 Xmas Hamper Delivery
Commited Funds not yet spent as at 24.11.20 |  |  |  |  | 22245
Proposed future projects Total |  |  |  |  | 50000
Financial Support in Kind (Appendix 2) |  | 941460
See details on sheet 2